## Risk Log
Risk Log Car_Quiz
Risk Identification and Description | [6 empty] | Risk Assessment |  |  |  |  | Risk Response
ID | Category | Risk Name | Risk Description & Details | Status | Identified By | Identification Date | Likelihood | Impact | Risk Level (L*I) | Risk Owner | Escalation | Risk Response Strategy | Action Details (effort & responsible) | Target Date | Traceability/Comments
RL01 | IT Security | Indisponibilitate baza de date locala | Din cauza indisponibilitatii serverului SQL local (CONDITION), se poate intampla ca intrebarile sa nu se incarce (EVENT), ceea ce va duce la blocarea functionarii quiz-ului (IMPACT). | Approved | Fratila Alexandru Daniel | 01.06.2026 | 3 | 4 | 12 | Fratila Alexandru Daniel | No | Reduce | Implementarea unui mecanism de exceptie care asigura functionarea aplicatiei prin incarcarea unei liste vide. (efort: 1 zi-om, responsabil: Fratila Alexandru Daniel) | 10/06/2026 | Identificat in faza de planificare, aliniat cu Project Charter.
RL02 | Business | Erori de calcul in strategii | Din cauza complexitatii formulelor de penalizare (CONDITION), se poate intampla ca punctajul sa fie calculat eronat (EVENT), ceea ce va duce la evaluarea incorecta a utilizatorului si nemultumirea acestuia (IMPACT). | Approved | Fratila Alexandru Daniel | 01.06.2026 | 2 | 4 | 8 | Fratila Alexandru Daniel | No | Reduce | Acoperirea codului cu o suita completa de teste unitare automate. (efort: 2 zile-om, responsabil: Fratila Alexandru Daniel) | 19/06/2026 | Identificat in faza de planificare, aliniat cu Project Charter si planul de testare.
Note on B5: The risk identifier. It should be numbered sequentially.
Note on C5: Categories of risks related to the area affected by the risk (e.g. Business, IT, People & Organisation, External and Legal, Sustainability, Data Protection, IT Security>
Note on D5: A short title for the risk.
Note on E5: A description of the risk that may occur in the project and its causes. What kind of problems will the risk result in and risk dependencies. A structured formulation of the opportunity or threat in the form of (route) Cause – Risk –Effect, along with potential risk inter-dependencies.
Note on F5: The risk status can be any of the following: Proposed: This is the initial status. Use this while the risk is still being specified. Assessing: Use this status to initiate an assessment. Waiting for Approval: Use this to request approval. Before applying this status, make sure the assessment is complete and the estimates are reliable. Approved: This status is set once the risk possibility has been accepted. Rejected: This status is set if the risk was rejected as not relevant. Closed: This status is set once the risk has been managed (e.g. mitigation )
Note on G5: The person who identifies the risk.
Note on H5: The date when the risk was identified.
Note on I5: A numeric value denoting the estimate of the probability that the risk will occur. The possible values are: 5=Very high 4=High 3=Medium 2=Low 1=Very low
Note on J5: A numeric value denoting the severity of the impact of the risk (should it occur). The possible values are: 5=Very high 4=High 3=Medium 2=Low 1=Very low
Note on K5: The risk level is the product of the likelihood and impact (RL=L*I).
Note on L5: The person accountable for the management and monitoring of this risk.
Note on M5: To be escalated to the Directing or Steering Layers: Yes or No.
Note on N5: The available strategies to deal with the identified risks are: - Avoid: risk avoidance, working the project or project plan around those conditions or activities which introduce the risk; - Reduce: risk mitigation or reduction through the proactive implementation of risk reduction activities; - Accept: acceptance of the risk. In this cases, contingency plans can also be defined in case the risk occurs; - Transfer/Share: transfer or share a risk with other entities, e.g. through insurances, sub-contracting etc.
Note on O5: Description of the action: objective of the action, scope, deliverables, person responsible and effort estimates.
Note on P5: The date that the action is expected to be implemented.
Note on Q5: The ID(s) of the task (in the Project Work Plan) implementing the risk actions, or/and the IDs of related change, issue or decisions log entries. Any additional information related to the risk approval (e.g. date) or related to the risk actions (activities).